Republic of Albania

Ministry of Finance and Economy

STRENGTHENING QUALITY OF AUDITING AND REPORTING PROJECT - ALBANIA

Terms of Reference

for

# Development of accountancy services and public awareness and Forensic accounting for accounting profession,

# Ref. No. SQARP-AL-QCBS-2.2

# 1. Background

Over the past two decades, Albania has experienced rapid growth while mitigating macro-financial vulnerabilities that emerged after the Euro-area crisis.

Despite recent reforms in the business regulatory framework, Albania still has further progress to make to modernize and improve its business environment and to ensure a proper enforcement of the improved regulatory framework. The Government of Albania (GOA) has taken some measures to improve the overall business climate in the country by streamlining business procedures through e-government reforms and by undertaking comprehensive structural reforms to both improve relevant legislation in a variety of sectors and lower the fiscal burden on companies. In addition, the GOA aims to strengthen the quality of and increase confidence in corporate financial reporting, as well as to ensure the reliability of financial information provided by corporate entities, including state-owned enterprises.

The 2019 WB Accounting and Auditing Report on Observance of Standards and Codes (A&A ROSC) update confirmed that Albania has made satisfactory progress in improving corporate financial reporting; however, it noted that further efforts are needed. The 2019 A&A ROSC Update noted that GOA should continue to work to close the gaps and converge its corporate financial reporting statutory framework closer with the EU’s acquis communautaire relating to company law, financial reporting, auditing, financial market, and financial institutions. Based on the 2019 A&A ROSC recommendations the Country strategy and Action plan (CAP) was revised in 2020 to include an extended reform agenda until 2023, setting out an updated strategy and action plan with a clear program of further reforms to enhance Albania’s legal framework in line with EU acquis, institutions, accounting and audit profession, and the Corporate Financial Reporting (CFR) in general.

Reform implementation in Albania is bringing important transformations throughout the CFR ecosystem, to the benefit of economic growth, financial stability, and taxation.

While the previous two projects CFREP and EQ FINREP covered a lot of ground and secured important results, prominent issues and priorities remain to be tackled and reforms initiated need to be advanced further to achieve and sustain results more fully. In order to address these issues and priorities the updated CAP explores several areas of attention:

As Albania has made good progress in developing the statutory framework for corporate financial reporting in recent years with amendment of the Audit Law in 2016 and enactment of the new Accounting Law in 2018, the GOA intends to continue to work to close the gap and fully converge its corporate financial reporting statutory framework with the EU legislation; this is generally a moving target as EU legislation is being permanently modernized, the priority of the Government is to be able to comply with the legislation in substance by the time of negotiations with the EU. The proposed project will continue to assist the GOA in the legislation convergence and build sustainable capacity for this process to continue when needed after the project completion.

Those terms of reference are provided under the Strengthening Quality of Auditing and Reporting Project (SQARP), which builds on and continues the reforms implemented under CFREP and EQFINREP projects.

The SQARP is funded by the Swiss State Secretariat for Economic Affairs (SECO). The SQARP’s objective is to strengthen the relevant stakeholder’s capacity to improve, apply and enforce corporate financial reporting in line with good international standards and practices in Albania. Developed based on a programmatic approach to improve the enforcement of corporate financial reporting in Albania, SQARP will provide the necessary underpinning for the continued reform in this area and will build on and reinforce previous reform work, support the implementation of improved laws and bylaws and other priority reforms reflected in the updated  CAP.

The SQARP is designed to be implemented by the GOA under a Recipient-Executed (RE) grant agreement and by the World Bank (WB) under a Bank-Executed grant (BE).

- The responsibility for the implementation of recipient executed activities is with key stakeholders, project coordination and day-to-day project management with the Ministry of Finance and Economy (MoFE), while the National Steering Committee (NSC) will have an overall oversight role. The Deputy Minister of MoFE, in his capacity as responsible for financial reporting reforms in Albania and Chair of the NSC, will be accountable for progress in project implementation.

- Fiduciary aspects of the trust fund management, including procurement and financial management, are handled by the General Directorate of Financing and Contracting of EU, WB and other donors funds (GDFC) at the MoFE.

- The project includes the provision of both technical and financial resources to strengthen the reform implementation capacity of the reform implementation group, specifically a local project coordinator and an international strategic consultant.

2. Objectives of the assignment

These Terms of Reference cover activities under Component 2 of SQARP project which aims to improve the capacities of the accounting profession in Albania to export accounting services and to develop skills in the forensic accounting.

Under this component support will be provided to various stakeholders in increasing their knowledge, know-how and capability in areas that provide the opportunity to export accounting services internationally, to the benefit of the profession and the economy.

- Stakeholders for this component will include IKM as a direct beneficiary and the MoFE as supporting the project management. From this assignment regarding the outsourcing of accounting services, it is expected to benefit the certified accountants (CA)/small and medium sized practices (SMPs), statutory auditors and audit firms that provide accounting services. Regarding the forensic accounting assignment it is expected to benefit the certified accountants (CA)/small and medium sized practices (SMPs).

This assignment should contribute to achievement of the following SQARP’ results and indicators:

- The Albanian accountancy profession is better equipped to compete internationally in exporting accountancy services;

- Aspiring professional accountants are qualified in line with good international practice  and are able to export improved accountancy services internationally;

- The Forensic accounting certificate program is operational;

By the end of the project, the IKM is expected to be better equipped to promote export of accounting services and the Forensic accounting certificate to be developed.

The MoFE, which chairs the Reform Implementation Group (RIG), is seeking on behalf of IKM, an experienced international consultancy firm (hereafter referred to as the Consultant) that has the necessary capabilities to achieve the objectives of the proposed activities.

- Scope of work

  - Design of the training program and preparation of the training materials based on market research and gap analysis.

    - Based on the gap analysis report to be put at the disposal of the Consultant by the Consultant responsible for the market research, which will identify the skills required by the international market and the actual capabilities of the local service providers, the Consultant will identify the criteria for selecting the target group who will attend the training.

    - Based on the results of the assessment performed in phase 1, the Consultant will design the training curricula which will enhance the capabilities of certified CAs/small and medium sized practices (SMPs) and statutory audit firms to export their services. The curricula will be a combination of technical and soft skills criteria. The curricula prepared will support the recognition of the training program from an international organization distinguished in accountancy education.

The training curricula must contain as a minimum the following.

    - Intermediate Financial Reporting skills, including relevant IFRS on the services to be exported. The extent of those topics will be based on the results of Gap Analysis and IKM confirmation

    - Basis of Taxation (training in the fiscal legislation will cover systems of 3-4 countries recommended as result of the market research assessment)

    - Accounting Software that will be used following the gap analysis. It is worth highlighting that software capabilities will be developed only in the processes that will be outsourced (i.e., payroll process, account receivable management etc.

    - Training on the SMP management guide (Guide to Practice Management for Small- and Medium-Sized Practices | IFAC)

    - Soft skills including but not limited to Project Management, how to do business, time management, delegation etc.

    - Training materials (PowerPoint Presentations, Word documents, PDFs, etc.) should be supported with requisite literature in English or translated. The training materials and case studies will be prepared in English and Albanian. The consultant should cover the cost of translation.

  - Training organization and delivery of Training of the Trainers (ToT) for the training to enhance the capabilities for the Outsourcing of accounting services, IFRS Diploma and Forensic Accounting trainings.

    - The consultant will prepare a work plan on how the training agenda will be delivered for all the activities. The consultant will provide criteria for the selection of trainers and provide a work plan on ToT delivery for the following courses: the training to enhance the capabilities for Outsourcing of accounting services, IFRS Diploma and Forensic Accounting trainings. The consultant will assess the institutional framework of IKM and identify if there are changes necessary to ensure that the new services offered by the members are properly supervised. Provide technical assistance to the staff of IKM regarding the changes in international standards applicable to the exporting of professional services.

    - Based on the criteria provided, the consultant in collaboration with IKM will select the local potential trainers for all the activities.

    - The consultant will deliver three “training of trainers (ToT)” courses for IKM selected trainers. During these training courses the consultant will facilitate the facilitating methodologies and techniques for those trainings. Training of the trainers’ sessions will be offered to a maximum of 15 trainers for each activity (that is, (i) training to enhance the capabilities of certified accountants and statutory audit firms that will export their services, (ii) IFRS Diploma, and (iii) Forensic Accounting Certificate) and will be carried out at IKM premises. The consultant has to cover all other costs, such as the cost of printing the training materials, translation of materials and interpretation, catering etc.

  - Delivery of training to develop the skills required to export services abroad.

    - The consultant will organize and deliver the training sessions in collaboration with the local trainers, trained as per activity 3.2 above, to 50 selected professionals. The training including all the modules should be no less than 40 hours.

    - At the end of training sessions all the participants will undergo an assessment for each module and based on the results achieved they will obtain a completion certificate separate per each module.

  - Strengthening of professional associations

IKM as a leading Accountants’ Association needs support to understand the international outsource of accounting services and the diversification of services offered CAs, CA candidates and accounting professionals. The consultant will assist IKM with the following activities:

    - The Consultant will facilitate the organization of a study visit to professional body/ies or other professional firm(s) of a Member State for selected members of IKM and other Project’s stakeholders, to take experience services offered by similar companies. The consultant will cover travel costs (economy class only) and for subsistence and accommodation, at the level of applicable EU per diem rates.

    - The consultant has to establish communication channels with key stakeholders in each country, as recommended by a research assessment report for the companies in Albania that will be ready to export their services. This activity will be concluded with an awareness activity (conference) in Albania with representatives from key stakeholders (Chamber of Commerce, companies and others from the identified countries, where accounting services can be outsourced, companies in Albania that will be ready to export their service, Ministry of Finance and Economy, World Bank, etc.). IKM staff will be part of this process and communication among stakeholders will be agreed with IKM.

    - As part of this activity, the consultant will design a Programme to enhance the IFRS capabilities of the accounting professionals, CA candidates and CAs, and for that reason a module on IFRS diploma needs to be designed, aligned to good international and European practice (e.g., ACCA’s DipIFRS, AICPA IFRS Certificate etc.). The consultant will prepare the curricula for the IFRS diploma including but not limited to:

      - Recognize the underlying concepts and principles of IFRS.

      - Identify the required format and content of a complete set of financial statements, including required footnote disclosures.

      - Identify the presentation and disclosure requirements of a statement of cash flows, including the proper classification of operating, financing, and investing activities.

      - Indicate and apply the requirements of new standards on revenue recognition (IFRS 15) and leases (IFRS 16).

      - Identify the classification, recognition, measurement, and disclosure of common financial statement assets and liabilities.

      - Identify and account for an impairment loss with respect to a nonfinancial asset.

      - Recall required disclosures for related parties and events after the reporting period.

      - Recognize the accounting treatment applied to share-based payments and employee benefits.

      - Recall accounting requirements for business combinations, joint arrangements, and investments in associates.

      - Identify and calculate tax amounts to be recognized in the financial statements.

      - Recall the accounting requirements applicable to entities that transact in or keep accounting records in foreign currency.

      - Indicate how to measure fair value when required by IFRS standards.

      - Examine the fundamental requirements of IFRS on a standard-by-standard basis.

      - Provide guidance on how to use IFRS in practice.

    - The consultant will prepare the modules and training materials, in English and Albanian. A minimum of 10 case studies will be required for each module.

    - A pilot training will be delivered jointly by the consultant and the trained trainers (no less than 120 hours) for 2 groups (25 members for each group), to be continued in the future with the entire membership.

    - At the end of training sessions all the participants will undergo an exam to be awarded the corresponding diploma or certificate. The Diploma in International Financial Reporting will be assessed by a single three-hour in person exam. The consultant will develop the exam structure, exam questions and respective answers, and will conduct the examination process and assessment in collaboration with IKM.

  - Development of forensic accounting program

    - The consultant will produce a policy paper to establish the eligibility criteria and the certification path to get certified as a forensic accountant.

    - The consultant will develop the curricula for the fundamental forensic accounting certificate, including the timing and syllabus for each training session. The training curricula will contain the following modules, which may change subject to agreement with IKM:

- Introduction to Forensic Accounting

- Crime and Economy

- Fraud Detection Techniques

- The Investigative Process

- Gathering Evidence

- Obtaining & Evaluating Non-Financial Evidence

- Interviewing Financially Sophisticated Witnesses

- Fraud Risk Assessment

- Fraud Prevention

- Bankruptcy

- Electronic Data Analysis

- Business Damages Concepts and Calculations

- Individual Damages Concepts and Calculations

- Intellectual Property Damages Concepts and Calculations

- Mergers & Acquisitions

- Family Law and Divorce Engagements

- Financial Statement Fraud, Corruption, and Asset Misappropriation

- Fraud Provisions and Engagements

- Valuation Practices in Forensic Engagements

The consultant will provide recommendations on developing more advanced forensic accounting modules.

    - The consultant will prepare the training materials to support the forensic accountant certificate. The training materials will be based on best international practices. The consultant may deem it appropriate to consult and agree with other international bodies to support the preparation of the materials. Materials will be prepared in English and Albanian.

  - Deliver the forensic accounting program.

    - In close cooperation with IKM the consultant will organize the training on forensic accounting. The consultants will agree with IKM about the training arrangements and schedule. These training courses will target the individual members of IKM interested in obtaining a forensic accountant certificate and will be incorporated in the CPD route of IKM. The cost for organizing this training should be covered by the consultant, including room rental, printing, translation and interpretation, catering and any other logistic necessary to carry out the activity. The training will ensure that the participants will acquire solid theoretical and practical knowledge about forensic engagements. The consultant will organize and deliver the training sessions in collaboration with the local trainers, trained as per activity 3.2 above, to 50 selected professionals. The training including all modules should be no less than 60 hours.

    - A formal assessment of knowledge will be organized at the end of the training in cooperation with IKM and based on the results a certificate will be given. The consultant will consult IKM on the approach to be followed to the certificate be legally recognized in Albania.

    - To ensure an endorsement from all interested stakeholders for the usage of the forensic certification, the consultant will organize an awareness activity with all the beneficiaries of forensic engagements, such as business community, judges, prosecutors, attorneys, and judicial police, accounting and auditing profession.

- Terms

The assignment is expected to start in September 2023.

The activities described in these TORs are expected to be completed within a period of 20 months, following the signing of the consultancy contract. Specifically, the consultant is expected to perform the activities within the deadlines described in the “Deliverables” section.

The expected level of effort is a maximum of 232 man-days spread during the implementation period. Is desired that the International Consultancy company arrange for this assignment a project team comprised of international and locally qualified staff.

The consultant’s experts are not required to be located all the time in Albania, though it is expected that the core members of the project team of the consultant will visit the country as necessary, but not less than sixteen times with at least 4 days per each time during the implementation period. The timing and frequency of visits will be agreed beforehand with IKM.

- Reporting and Deliverables

The Consultant will carry out the work in 3 phases:

  - A planning phase.

  - An implementation phase.

  - Final Phase.

5.1 Planning Phase

An inception report will contain a comprehensive work plan, following a preliminary assignment analysis, covering all tasks, including but not limited to, a full description of work to be performed and methodology followed, lists of documents to be reviewed, persons/institutions to be interviewed, timetables of deliverables including visits and training/awareness events. The work plan will have to be agreed with beneficiaries. The work plan needs to be submitted within 30 days after the signing of the contract.

5.2 Implementation Phase:

The consultant is expected to produce the following deliverables:

|  | Deliverables under component 3.1: Design of the training program and preparation of the training materials based on market research and gap analysis | Delivery date |
| --- | --- | --- |
| 1 | Identification of the target group who will receive the training – based on the gap analysis performed in phase 1 the consultant will identify the criteria for selecting the members who will attend the training. The criteria and the list of participants will be agreed with IKM. | 1 month from contract signature |
| 2 | Training curricula to enhance the capabilities of CA and SA firms to export their services. The curricula will be a combination of technical and soft skills criteria. Training materials (PowerPoint Presentations, Word documents, PDFs, etc.) should be supported with requisite literature in English or translated. The training materials and case studies will be prepared in English and Albanian. | 2 months from contract signature |
|  | Deliverables under component 3.2: Training organization and delivery of Training of the Trainers for all activities | Delivery date |
| 1 | Work plan on how the training agenda will be delivered for all the activities. The consultant will provide criteria for the selection of trainers and provide a work plan on ToT delivery. The consultant will assess the institutional framework of IKM and identify if there are changes necessary to ensure that the new services offered by the members are properly supervised. | 4 months from contract signature |
| 2 | Based on the criteria provided the consultant in collaboration with IKM will select the local and/or international trainers for all the activities. | 4 months from contract signature |
| 3 | The consultant will deliver the “training of trainers (ToT)” courses for IKM selected trainers. | 5 months from contract signature |
|  | Deliverables under component 3.3: Delivery of training to develop the skills required to export services abroad | Delivery date |
| 4 | The consultant will organize and deliver the training sessions in collaboration with the local trainers to 50 selected professionals. The training including all the modules should be no less than 40 hours. | 5 months from contract signature |
|  | At the end of training sessions all the participants will undergo an assessment for each module and based on the results achieved they will obtain a completion certificate separate per each module. | 5 months from contract signature |
|  | Deliverables under component 3.4: Strengthening of professional associations | Delivery date |
| 1 | A study tour in another analogue professional organization will be organized to get experience of other services offered from member of international professional organization. | 6 months from contract signature |
| 2 | An awareness activity (conference) will be organized in Albania with representatives from key stakeholders (Chamber of Commerce, companies, and others from the identified countries where accounting services can be outsourced, companies in Albania that will be ready to export their service, MoFE, World Bank, etc.). | 6 months from contract signature |
| 3 | The consultant will design a program to enhance the IFRS capabilities of the accounting professionals, CA candidates and CAs, and for that reason a module on IFRS diploma needs to be designed, aligned with international accounting organizations and associations (such as ACCA, AICPA etc.). | 7 months from contract signature |
| 4 | The consultant will prepare the curricula for the IFRS diploma. | 11 months from contract signature |
| 5 | The consultant will prepare the modules and training materials, in English and Albanian. A minimum of 10 case studies will be required for each module. The training materials will be property of IKM. | 11 months from contract signature |
| 6 | A pilot training will be delivered (no less than 120 hours) for 2 groups (25 members for each group), to be continued in the future with the entire membership. | 12 months from contract signature |
| 7 | At the end of training sessions all the participants will undergo an exam to be awarded the corresponding diploma or certificate. The Diploma in International Financial Reporting will be assessed by a single three-hour in person exam | 13 months from contract signature |

|  | Deliverables under component 3.5: Development of forensic accounting program | Delivery date |
| --- | --- | --- |
| 1 | The consultant in coordination with IKM will set up the entry requirement criteria to get certified as forensic accountant. The consultant will prepare the entry requirements criteria, promote the program, and ensure that a minimum of 50 accountants will attend the program. | 11 months from contract signature |
| 2 | The consultant will develop the curricula for forensic accounting certificate, including in here the timing and syllabus for each training session. The consultant may provide recommendations as well on how the curricula can be harmonized with internationally recognized forensic certifications and / or adhere to international organizations specialized in forensic. | 13 months from contract signature |
| 3 | The consultant will prepare the training materials to support the forensic accountant certificate. Materials will be prepared in English and Albanian. The materials must contain theoretical and practical examples. Per each module a minimum of 10 real life examples with respective methodology and deliverables need to be part of the training materials. | 14 months from contract signature |
|  | Deliverables under component 3.6: Deliver the forensic accounting program | Delivery date |
| 1 | In close cooperation with IKM the consultant will organize the training on forensic accounting. | 14 months from contract signature |
| 2 | The consultant will organize and deliver the training sessions in collaboration with the local trainers to 50 selected professionals. The training including all modules should be no less than 60 hours. | 17 months from contract signature |
| 3 | A formal assessment of knowledge will be organized at the end of the training in cooperation with IKM and based on the results a certification will be given. The consultant will consult IKM on the approach to be followed to the certificate be legally accepted. | 18 months from contract signature |
| 4 | To ensure an endorsement from all the stakeholder for the usage of the forensic certification, the consultant will organize an awareness activity with all the beneficiaries of forensic engagements, such as business community, judges, prosecutors, attorneys, and judicial police. The consultant is responsible for organizing the closing event and ensure the participation of the stakeholders. | 19 months from contract signature |
| 5 | Final Report | 20 months from contract signature |

Note:

- Each of the abovementioned deliverables should be approved by the Contract Coordinator within 5 Business Days.

- All the documents will be delivered in both English and Albanian language.

- Institutional and organizational arrangements

The Consultant will report to IKM and the Ministry of Finance and Economy.

During all implementation time the consultant will maintain frequent communication with the local coordinator and representatives of all parties involved.

For administrative matters, the consultant will communicate as necessary with GDFC.

IKM will provide the consultant with facilities, and office space as necessary for the performance of the consultancy assignment. The other facilities to cover the training activities are described in the relevant sections.

- Qualifications

  - Consulting firm/ The Consultant

The International Consultancy firm/Consortium shall have the following expertise and experience:

- Should be active and operational at the moment of proposal submission;

- At least 10 years of core experience in accounting and auditing;

- Proven experience in projects in training design, development of curricula and supporting educational materials;

- Previous experience collaborating with Accountancy professional organizations to develop training curricula and educational materials.

The consulting firms participating in the bid will be assessed in order to determine a shortlist comprising the most qualified candidates. The criteria to be used for shortlisting will be the following:

(i)	General Qualifications, including core business and years in business (30 points);

(ii)	Relevant experience, including previous experience in the field of assignment (70 points);

The CVs of Key experts will not be evaluated during the shortlisting process.

7.2 Key Experts

The International Consultancy company should arrange a project team comprised of 3 international experts. One of the key experts will act as the team leader. International key expert(s) need to demonstrate these minimum requirements:

Key expert 1/Team leader:

- At least a master’s degree in Economic Sciences (Accounting, Auditing, Finance, etc.) or an equivalent professional title;

- At least 10 years professional experience in accounting and /or auditing in EU countries implementing IFRS or other relevant international standards;

- At least 5 years of teaching experience and training delivery (in a Member State is preferred) in accounting and/or auditing;

- At least 5 years of managing experience as a team coordinator/project manager;

- Experience in projects is a must;

- Very good knowledge of English Language;

- Computer literacy;

Key expert 2 (responsible for IFRS Diploma):

- At least a master’s degree in Economic Sciences (Accounting, Auditing, Finance, etc.) or an equivalent professional title;

- At least 10 years professional experience in accounting and /or auditing in EU countries implementing IFRS or other relevant international standards;

- At least 5 years of teaching experience and training delivery (in a European country is preferred) in accounting and/or auditing;

- Experience in projects is a must;

- Very good knowledge of English Language;

- Computer literacy;

Key expert 3 (responsible Forensic Accounting certification):

- At least a master’s degree in forensic accounting or an equivalent professional title;

- At least 10 years professional experience in Forensic Accounting in EU countries implementing relevant international standards;

- At least 5 years of teaching experience and training delivery (in an European country is preferred) in Forensic Accounting;

- Experience in projects is a must;

- Very good knowledge of English Language;

- Computer literacy;

- Restrictions

In addition to the standard conflict of interest restrictions specified in the consulting contract, all materials created under this Contract will remain the sole property of MoFE and IKM. Re-use of the materials will require formal, written approval.

The Consultant shall have no material interest in any of the outputs of this assignment.

On the commencement of the assignment, the Consultant will jointly prepare with the MoFE and IKM a statement of confidentiality that will bind the Consultant to nondisclosure of any sensitive information that he/she may become knowledgeable of during the assignment.

The terms of this agreement shall be made consistent with the relevant privacy laws of the Republic of Albania.

- Selection

The service will be selected under the provisions of the World Bank Procurement Regulations for IPF Borrowers (Procurement Regulations), in investment project financing Goods, Works, Non-Consulting and Consulting Services November 2020, in accordance with Quality and Cost Based Selection Method (QCBS), Lump-Sum Contract. The Bank requires that firms or individuals involved in Bank IPF procurement shall not have conflict of interest.

https://cfrr.worldbank.org/programs/sqarp